## MR
Michael Roark | Date | Accomplishments Summary | Time (hours) | Total Time (hours)
| 2017-09-01 | researched node.js | 0.75 | 12.75
| 2017-09-05 | created sideshow investigated Node.js and devised possible trivia data schema. Investigated grunt and npm package handling. | 1.25
| 2017-09-08 | Began prototyping a REST api in Node.js for possible use in the project. Main goal was to get comfortable with Node.js in general. | 1.5
| 2017-09-09 | Worked on feasibility report. | 1.75
| 2017-09-17 | Compiled feasibility reports. Learned the actions sdk through reading and attempting to prototype an action. | 6
| 2017-09-26 | Starting charting mathflash | 1.5

## BP
Ben Pister | Week Work Period | Accomplishments Summary | Time (hours) | Total Time (hours)
| 2017-09-02 | Researched Node.js execution | 1 | 24.5
| 2017-09-04 | Researched Node.js testing frameworks and Google Actions | 2
| 2017-09-08 | Building group website | 1
| 2017-09-09 | Worked more on group site. Worked on site setup - much of it built - still could use beautification | 6.25
| 2017-09-12 | Restructuring website with conforming layout and much better background | 3.25
| 2017-09-14 | Researched for the Feasibility Tasks. Worked out padding issues and smoother layout | 3
| 2017-09-18 | Altered group site to match prof request | 2.25
| 2017-09-23 | Added text shadow to team info text overlaying braille image Added Gantt Chart of Project Progress Worked additionally to enable horizontal scroll of image, unsuccessfully | 1.75
| 2017-09-24 | Still working on horizontal scroll, using an html table. Continued work on horizontal scroll for gantt image. Used a div instead of a table, worked: task completed. | 4

## JO
Joseph Olin | Date | Accomplishments Summary | Time (hours) | Total Time (hours)
| 2017-09-02 | Filled out shared Google Calendar and researched Google Actions | 2.25 | 18
| 2017-09-08 | Continued email correspondence with APH and Team LER (correspondence has been consistent throughout the week). Started on September timesheet template to keep track of team member hours and accomplishments. Worked on a Google Actions SDK tutorial | 4
| 2017-09-09 | Worked on Feasability Report | 1
| 2017-09-12 | Continued working on Feasibility Report | 2
| 2017-09-13 | Continued working on Feasibility Report. Updated group timesheet | 1
| 2017-09-15 | Began researching Google Actions in further detail | 1
| 2017-09-19 | Created PPT for presentation | 0.75
| 2017-09-22 | Emailed APH Math Flash Game code to other team members. Began looking over Math Flash Game. Began researching Node.js more fully | 0.75
| 2017-09-29 | Emailed Laura at APH to get reporting preferences. Began monthly report for September. Started updating monthly time sheet spreadsheet | 3.75
| 2017-09-30 | Continued working SRS report. Edited monthly report and monthly timesheets | 1.5